## <Sprint Name> Test Summary
ZUPLOG Sprint 2.3.9 | [5 empty] | Assigned to: |  | QA
| JIRA ID | Summary | Priority | Type | Story Points | Assignee | Status | Test Cases Added / Updated | Test Cases Reviewed | Tested on Staging | Test Version | # of Test Cases | Pass | Failed | Passing Rate | Test Coverage
| ZUPLOG-1005 | Add marketing email to receive daily user reports | Medium | Task | 1 |  | Done | [8 empty] | #REF!
| ZUPLOG-1004 | Release Blocker: Contact selection in Send money | High | Bug | 1 |  | Done
| ZUPLOG-860 | Support distributed cache | Medium | Sub-task | 1 |  | Done
| ZUPLOG-727 | Remove Dart | High | Bug | 2 |  | Done | [8 empty] | #REF!
| ZUPLOG-997 | Tracking fixes | Medium | iOS | 3 | nn | In Progress
| ZUPLOG-972 | Make contact search work with/without umlauts | Low | Task | 3 | ds | In Progress | [8 empty] | #REF!
| ZUPLOG-971 | UITest for Send money | Medium | iOS | 2 |  | In Progress | [8 empty] | #REF!
| ZUPLOG-962 | Refresh token problem for same account on multiple devices | Low | Backend | 3 | dpavlovic | In Progress | [8 empty] | #REF!
| ZUPLOG-624 | Switch account if the user tries to see details of an account that is not selected | Low | Android | 2 | ds | In Progress | [8 empty] | #REF!
| ZUPLOG-590 | Integrate and implement UI testing | Medium | Android | 8 | dp | In Progress | [8 empty] | #REF!
| ZUPLOG-478 | Make app ready for distributed processing | High | Backend | 8 | dpavlovic | In Progress | [8 empty] | #REF!
| ZUPLOG-274 | Integrate Appboy push sdk to see how we can use it | Lowest | Android | 2 | ds | In Progress | [8 empty] | #REF!
| ZUPLOG-999 | Remove 'DE' validation while creating a contact. | High | Bug | 1 | fm | In Review | [8 empty] | #REF!
| ZUPLOG-996 | `Loading` screens to be consistent in whole app | Medium | iOS | 3 | nn | In Review | [8 empty] | #REF!
| ZUPLOG-995 | Refactor Navigation controller to fully support all iOS versions | Medium | iOS | 3 | an | In Review | [8 empty] | #REF!
| ZUPLOG-986 | Email check always on lower case | High | Backend | 1 | fm | In Review | [8 empty] | #REF!
| ZUPLOG-985 | Use local bank connections in updater method | Medium | Backend | 2 |  | In Review | [8 empty] | #REF!
| ZUPLOG-953 | Refactor Adjust Tracking | Medium | Sub-task | 2 |  | In Review | [8 empty] | #REF!
| ZUPLOG-952 | Refactor Appboy Tracking | Medium | Sub-task | 3 |  | In Review | [8 empty] | #REF!
| ZUPLOG-951 | Refactor Rest of Analytics Tracking | Lowest | Story | 5 | ds | In Review | [8 empty] | #REF!
| ZUPLOG-950 | Scrollable Dashboard | Medium | iOS | 2 | nn | In Review | [8 empty] | #REF!
| ZUPLOG-928 | Support full utf8 signs in DB | Medium | Backend | 3 | fm | In Review | [8 empty] | #REF!
| ZUPLOG-861 | Support distributed quartz jobs | Low | Sub-task | 5 | dpavlovic | In Review | [8 empty] | #REF!
| ZUPLOG-521 | Handle "null" in Appboy dashboard | Medium | Task | 1 | fm | In Review | [8 empty] | #REF!
| ZUPLOG-1000 | Draft an architecture proposal for a middle layer interface | Medium | Research | 8 | fm | Open | [8 empty] | #REF!
| ZUPLOG-1003 | Email input text fields should be all lower case | Medium | Android | 1 | GT | Done | Y | N | Y | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| ZUPLOG-968 | Ask users for reviews when they complete money transfer | Medium | Story | 5 | ma | Testing
| ZUPLOG-1001 | Customer service requests handling | Medium | Task | 3 |  | To Do
| ZUPLOG-998 | Tracking fixes | Medium | Android | 3 |  | To Do
| ZUPLOG-965 | Change UserManager to Repository | High | Task | 2 |  | To Do
| ZUPLOG-903 | Synchronize font in the app | Medium | iOS | 2 |  | To Do
| ZUPLOG-746 | Re-enable Internet connectivity | Low | iOS | 3 |  | To Do
| ZUPLOG-745 | UITest for new dashboard screens | Medium | iOS | 2 | an | To Do
| ZUPLOG-604 | PIN refactoring | Low | iOS | 3 |  | To Do
Test Results on this line | [10 empty] | TOTAL | #REF! | #REF! | #REF! | #REF! | #REF!
List of Bugs Found

## TAB #Template <JIRA ID> (<statu
Sprint | ZUPLOG 2.3.9 |  | User Story | Acceptance Criteria / Description |  | # of Test Cases | 5 | # of Failed | 0
Story ID | ZUPLOG-1003 |  | Email input text fields should be all lower case |  |  | Passed Test Percentage | 0% | # of Passed | 0
Epic | [5 empty] | Executed Test Case | 5 | # of Blocked | 0
Status | Testing |  |  |  |  | Version | Zuper-Staging 2.3.9.0(93) | Test not Run | 0
Component | Android |  |  |  |  | Devices and OS | Samsung J5 - Android 6.0.1 | Last TC Execution | Execution Date
TC ID | TC Type | Section | Summary | Preconditions | Step Actions | Test Data | Expected Results | Status | Notes | JIRA Ticket | Version | Actual Results
1003-01 | [10 empty] | Portal v0.34.a7e124e353fe

## Guildelines for Raising Issues
I. Raising a Bug on a Testing Story | [5 empty] | Define Priority
| On Test Case list |  |  |  |  | Blocker
|  | 1. Once the story is in Ready for QA, the tester can start on executing the test / test cases for that story |  |  |  | Critical
|  | 2. If the test case pass the test, mark the test case as "Pass" |  |  |  | Major
|  | 3. If the test case failed the test, mark the test case as "Fail" |  |  |  | Minor
|  | 4. If there is a bug found but not on the test case list, add the bug as test case on the spreadsheet |  |  |  | Trivial
On JIRA
Scenario 1
1. Once the test case is failed, move the Ready for QA story to the Failed column
2. A prompt will show on creating an issue with a type of "Bug"
3. Add the following details on the bug:
|  |  | A. Title / Summary | Be informative as possible
|  |  | B. Priority | Blocker, Critical, Major, Minor, Trivial
|  |  | C. Affects Version / s | Version/s the issue affects
|  |  | D. Fix Version / s | What version is will be fixed
|  |  | E. Bug Source | Usually: Internal, but other option is Client
|  |  | F. Description | Details of the bug:
|  |  |  | a. Build Version | where issue was encountered
|  |  |  | b. Pre-Condition | if needed, add conditions need to meet before starting the steps like accounts, browsers, etc
|  |  |  | c. Steps | Detailed steps to encounter the bug. Use the TC steps
|  |  |  | d. Actual Results | Current encountered output
|  |  |  | e. Expected Results | What is the expected output
|  |  |  | f. Attachments | supporting documents or images to help the devs in replicating the bug
|  |  |  | g. Others | other information which may help the devs
|  |  | G. Original Estimate | Put on how much time will the dev need to fix the issue(Ask Rachel or Dev assign to the story)
|  |  | H. Epic Link | Epic which holds the story being tested
|  |  | I. Sprint | Sprint where the bug will be fixed. Usually current Sprint
4. Click Create button
Output: A new bug will be created and will under To Do. Story will also go back to the To Do column
Scenario 2
1. Is another test case failed and finish Scenario 1
2. Click Create on JIRA header
3. Add the following details on the bug:
|  |  | A. Project | Make sure you are raising a bug on the correct project
|  |  | B. Issue Type | Select Bug
|  |  | C. Title / Summary | Be informative as possible
|  |  | D. Priority | Blocker, Critical, Major, Minor, Trivial
|  |  | E. Affects Version / s | Version/s the issue affects
|  |  | F. Fix Version / s | What version is will be fixed
|  |  | G. Bug Source | Usually: Internal, but other option is Client
|  |  | H. Description | Details of the bug:
|  |  |  | a. Build Version | where issue was encountered
|  |  |  | b. Pre-Condition | if needed, add conditions need to meet before starting the steps like accounts, browsers, etc
|  |  |  | c. Steps | Detailed steps to encounter the bug. Use the TC steps
|  |  |  | d. Actual Results | Current encountered output
|  |  |  | e. Expected Results | What is the expected output
|  |  |  | f. Attachments | supporting documents or images to help the devs in replicating the bug
|  |  |  | g. Others | other information which may help the devs
|  |  | I. Original Estimate | Put on how much time will the dev need to fix the issue(Ask Rachel or Dev assign to the story)
|  |  | J. Epic Link | Epic which holds the story being tested
|  |  | K. Sprint | Sprint where the bug will be fixed. Usually current Sprint
4. Click Create button
5. View the newly created bug
6. Click Add Link
7. Select Blocks on the This issue dropdown
8. Select the issue number of the Story
9. Click Link
Output: A new bug will be created and will under To Do. The bug will be linked to the story

## ONE PAGER #Template Test Cases
Story | ZUPLOG-1024 | Change Sign Up Flow |  | Version | Zuper-Staging 2.3.9.0(93) | # of Test Cases | 5 | Executed Test Case | #REF! | # of Passed | 0
Status | To Do | Component | Android | Devices and OS | Samsung J5 - Android 6.0.1 | Passed Test Percentage | #VALUE! | Last TC Execution | Execution Date | # of Failed | 0
TC ID | TC Type | Section | Summary | Preconditions | Step Actions | Test Data | Expected Results | Status | Notes | JIRA Ticket | Version | Actual Results
1024-01 | [10 empty] | Portal v0.34.a7e124e353fe
1024-02
1024-03
1024-04
1024-05
Story | ZUPLOG-1024 | Change Sign Up Flow |  | Version | Zuper-Staging 2.3.9.0(93) | # of Test Cases | 5 | Executed Test Case | #REF! | # of Passed | 0
Status | To Do | Component | Android | Devices and OS | Samsung J5 - Android 6.0.1 | Passed Test Percentage | #VALUE! | Last TC Execution | Execution Date | # of Failed | 0
TC ID | TC Type | Section | Summary | Preconditions | Step Actions | Test Data | Expected Results | Status | Notes | JIRA Ticket | Version | Actual Results
1024-01 | [10 empty] | Portal v0.34.a7e124e353fe
1024-02
1024-03
1024-04
1024-05